[Event Name]

[Date/Time]

[Location]

[ORGANISATION NAME]

EVENT DAY RUN SHEET

This template is a guide. Rearrange, edit, add or remove headings in each section to suit your event requirements.

Document created and developed by [Full Name] on behalf of [Organisation Name].

EVENT TEAM CONTACT LIST

| Position | Full Name | Phone Number |
| --- | --- | --- |

VIP, PERFORMERS & ACTIVITIES CONTACT LIST

| Position/Service | Full Name | Phone Number |
| --- | --- | --- |
| Key Note Speaker | Daisy Nguyen | 1234 567 890 |
| Colourful Faces | Jessie Singh | 1234 567 890 |
| Singer | Breanna Davidson | 1234 567 890 |

FOOD VENDORS CONTACT LIST

| Business Name | Full Name | Phone Number |
| --- | --- | --- |
| Bobs Burgers | Bob Dylan | 1234 567 890 |

CONTRACTORS & SUPPLIERS CONTACT LIST

| Company | Full Name | Phone Number |
| --- | --- | --- |
| Stop & Go | Jason Smith | 1234 567 890 |
| Better Stages | Felicity Tork | 1234 567 890 |
| Secure Security | Sam Safety | 1234 567 890 |
| Neat & Tidy | John Yusef | 1234 567 890 |
| Amusing Rides | Abby Dell | 1234 567 890 |

PACKING LIST (REMOVE EXAMPLES)

| Item | Qty | Notes |
| --- | --- | --- |
| A-frames |  |  |
| Banners |  |  |
| Bollards |  |  |
| Batteries |  |  |
| Cable ties |  |  |
| Clipboards |  |  |
| Event Pack of all Documents |  |  |
| Double adapter |  |  |
| Extension cord |  |  |
| First Aid kit |  |  |
| Gaffer tape |  |  |
| Gloves |  |  |
| Hazard tape |  |  |
| Highlighters |  |  |
| Incident report forms |  |  |
| Masking tape |  |  |
| Measuring tape |  |  |
| Mobile phone charger |  |  |
| Pens |  |  |
| Permanent markers |  |  |
| Roll of garbage bags |  |  |
| Scissors |  |  |
| Signage |  |  |
| Wipes |  |  |

RUN SHEET

| Pre-Event Day |  |  |  |
| --- | --- | --- | --- |
| 0900 | 1200 | Stage bump in | Felicity Tork |
| 1200 | 1400 | Marquee bump in | Felicity Tork |
| 1400 | 1500 | Event Pack Printing | Event Staff |
| 1400 | 1600 | Amusement rides arrival and bump in | Abby Dell |
| 1600 | 1700 | Collection of decorations, signage, information | Event Staff |
| 1800 | 2400 | Security – asset protection starts | Sam Safety |
| Event Day |  |  |  |
| 0000 | 0900 | Security – asset protection finishes | Sam Safety |
| 0900 | - | AV bump in |  |
| 0900 | 0930 | Bins delivered to site | John Yusef |
| 0930 | 1000 | Apply waste signage to all bins | Event Staff |
| 1000 | 1200 | Food Vendor arrival and bump in | Event Staff |
| 1100 | 1300 | Stallholder Vendor arrival and bump in | Event Staff |
| 1200 | - | Traffic management commences | Jason Smith |
| 1200 | 1400 | Activities Vendors arrive and bump in | Event Staff |
| 1545 | 1600 | Bianca Festival arrival | Event Staff |
| 1600 |  | Event starts |  |
| 1630 | 1700 | Bianca Festival Keynote Speech | Event Staff |
| 1700 | 2000 | Stage Program continues | Event Staff |
| 1800 | 1810 | Waste and recycling bin checks | Event Staff |
| 2000 | - | Event finishes |  |
| Post-Event Day |  |  |  |
| 2000 | 2200 | Stage and marquee bump out | Felicity Tork |
| 2000 | 2200 | Vendor bump out | Event Staff |
| 2200 | 2300 | All waste collected and removed from site | John Yusef |
| 2400 | - | Traffic management finishes | Jason Smith |